## Sheet1
Risk Details |  | Risk Identification | [6 empty] | Response Strategy | [5 empty] | Reflection
Risk ID | Date Identified | Name Of Risk | Risk Description | Scale of Severity | Scale of Likelihood | Impact | Owner | Stage Of Project | Strategy To Mitigate | Risk Occured | When did it occur | Details of what occured | Action Taken | Length Of Impact (HRS) | Future Risk
1 |  | DSE(Display Screen Equipment) | Staring at a computer screen for too long will have negative effects | Acceptable | Possible | Medium | All | Continuous | Plenty of breaks scheduled in order to rest eyes | Yes | Continuos | Eye strain at certain points from looking at the screen for too long | Took a break to give eyes a break fromt the screen light | 1 | Working from home has increased so this will always be a risk
2 |  | Slips, Trips and Falls | Untidy desk/home, accidents do happen | Tolerable | Possible | Medium | All | Continuous | Make sure that everything is tidy and put away to lower the risk of catching yourself on something | No | N/A | N/A | N/A | 0 | All about making your workspace as safe as possible
3 |  | Stress | Over-working with minimal breaks in between | Generally Unacceptable | Probable | High | All | Continuous | Regular breaks, talking about the plan with the team | Yes | End of Development | Began to feel tired and needed a break from certain issue that was occuring | Another member of the team peer programmed and helped to resolve the issue | 1 | This can increase due to working from home - it is crucial to keep up to date with your colleagues and co-workers
4 |  | Electrical Equipment(Maintainance) | Out of warranty items could be hazardous | Tolerable | Possible | High | All | Continuous | Check that equipment you're using is safe and not dangerous | No | N/A | N/A | N/A | 0 | Working from home has increased so youll need to keep an eye on your equipment to know when it will need replacing
5 |  | RSI(Repetitive Stress Injury) | Alot of typing and reading off a computer screen | Tolerable | Probable | Medium | All | Continuous | Regulat breaks again to rest limbs - comfy chair - ergonomic items around the desk to increase comfort | No | N/A | N/A | N/A | 0 | Going to be a cont risk
6 |  | COVID-19 | Global Pandemic | Tolerable | Not Likely | High | All | Continuous | Following the government advice and making sure to stay safe if going out | Yes | N/A | Sam had to take time away to take a test | I informed the team that this was happening and they accounted for it in the planning phase fo the proejct and caught me up when i was back | 1 | There is always the risk of a pandemic - hopefully what we have learnt from this one will help to deal with the next one
7 |  | Lack Of Knowledge | Certain areas of the project may require further research | Tolerable | Possible | Medium | All | Continuous | Troubleshoot and talk with team to peer programme to increase the knowledge | Yes | Development and Testing | Research into certain errors and docmentation was required | Peer programming and searching together to find the dolution to an issue that we were having | 0 | This will always be a risk - keep up to date with current documentation is crucial
8 |  | Merge Conflicts | Working in a team using Git could result in some of these | Acceptable | Probable | Medium | All | Continuous | Communicate with the team effectively to make sure everyone knows who is working on what document | Yes | Development and Testing | When merging into dev certain docs clashed with one another | We spoke with other members of the team to determine which of the conflicts to approve | 0 | Communication is vital to make sure that you are all working on the correct documents at the correct time
9 |  | Internet Connection | If the router crashes or you lose connection during meeting | Tolerable | Possible | Medium | All | Continuous | Sometimes a reset of the router every now and again can help - also make sure to have contact info for provider on hand | No | N/A | N/A | N/A | 0 | This is always a possibility so making sure that we have a contingency availiable is crucial
10 |  | Scope Creep | Delivering a product that does not meet the spec first | Generally Unacceptable | Not Likely | High | All | Development | Refer to the project spec regularly and update plans according to the spec | No | N/A | N/A | N/A | 0 | Always clarify the MVP to make sure that you all understand the brief and you are on the same page as the client
11 |  | Time Management | Not finishing tasks or sprints within the alloted time | Tolerable | Possible | Medium | All | Continuous | Planning time effectively at the start of the prject - be realistic with thr goals that you set woith tht team | No | N/A | N/A | N/A | 0 | In the future teams need to be aware of the sprint times and make sure that if something is a must - it is completed without hesitations
12 |  | Tech Incompatibility | New software downloads | Generally Unacceptable | Not Likely | Medium | Mo | Continuous | Always download the latest stable version and read up on compatibility with current installed software | Yes | End of Development | React-Scripts needed updating | Contacted Sav to resolve issues | 1 | Compatibility may change with updates so always check regulalary to make sure that everything still workis tandam
13 |  | Childcare | Working from home with young child | Tolerable | Not Likely | High | Sam | Continuous | Making sure that adequate and safe childcare is arranged for when it is needed | No | N/A | N/A | N/A | 0 | I may not be able to arrange for childcare, and it may be something to discuss with employer
14 |  | Lack of Communication | Team not communicating effectively what they are working on | Generally Unacceptable | Not Likely | High | All | Continuous | Stand up meetings and regular catch ups to ensure that we continue to work off the same sheet | No | N/A | N/A | N/A | 0 | Working in a team you need to make sure that you are staying in touch and communicating effectivley
15 |  | Unplaned Work to be Acccmodated | Something that we hadnt planned for crops up and needs to be dealt with | Tolerable | Possible | Medium | All | Development | Make sure that we are accounting for this in the sprint time - communicate with the team - adjust what needs to be done | Yes | Development | some of the schemas needed to be updated and back end functions added | Another branch was made to update them and then, hotflixed it back into the dev when it was complete | 2 | This can always be a risk as the project evolves
16 |  | Insufficient Story Testing Pre-Live Date | Lead to bugs and errors in the final product | Generally Unacceptable | Not Likely | High | All | Testing | Make sure that testing covers the correct outputs and assertions are effective in testing what is outputted | No | N/A | N/A | N/A | 0 | Bugs can be sent to the live version
17 |  | Health CheckUps | Loss of time on the project can occur with unexpected changes to schedule | Acceptable | Probable | Low | Rob | Development | Make sure that we let other members of team as well as trainee and line manager know | Yes | 3/3/2021 - Development | Rob had a appt booked - didnt impact the project time | Rob informed the team before the appt and there was no impact on the project time | 0 | This can occur in all walks of work so it is something that needs to be accomodated for
| Risks Occured | Impacted Time
| 7 | 6